## Projects Overview
Projects Overview
Milestones |  | Progress | Start | End | Notes
Project Update | 100% | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | 2016-09-16 | 2016-09-27
Milestone1 | 100% | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦ | 2016-09-28 | 2016-10-07
Milestone2 | 0.01% |  | 0 | 0
Milestone3 | 0.01% |  | 0 | 0
Milestone4 | 0.01% |  | 0 | 0
Formulas:
Start = MAX(IF((Tasks[Milestones]=Projects[[#This Row],[Milestones]])*(Tasks[Start]>0),Tasks[[Start]:[End]]))
End = MAX(IF((Tasks[Milestones]=Projects[[#This Row],[Milestones]])*(Tasks[Start]>0),Tasks[[Start]:[End]]))
Task Details
TIP: Double-click project to view and enter associated tasks.

## Task Details
Task Details
Start | End | Milestones | Task | Done | Notes
2016-09-16 | 2016-09-16 | Project Update | Select Team | 1
2016-09-16 | 2016-09-27 | Project Update | Project Proposal | 1 | Submitted before the milestone 1
2016-09-28 | 2016-10-07 | Milestone1 | Project Plan | 1
2016-09-28 | 2016-10-07 | Milestone1 | Assign Roles and responsibilities | 1
2016-09-28 | 2016-10-07 | Milestone1 | User Stories | 1
2016-09-28 | 2016-10-07 | Milestone1 | Requirement Analysis | 1
2016-09-28 | 2016-10-07 | Milestone1 | Architecture Design | 1
2016-09-28 | 2016-10-07 | Milestone1 | Mockups | 1
2016-09-28 | 2016-10-07 | Milestone1 | Design Document | 1
2016-10-07 | 2016-10-07 | Milestone1 | Setup Github Repository | 1
|  | Milestone2 | Updated design docs
|  | Milestone2 | Develop Prototype
|  | Milestone2 | UI implementation, and implementing selected functionality
|  | Milestone2 | Draft Test Plan
|  | Milestone2 | Develop source Code
|  | Milestone2 | Upload Code into Git repository
|  | Milestone2 | Present the project to the class
Projects Overview
TIP: Double-click in Done column when task is complete.